| Category | Task | Status | Completed | Who | Notes |
| --- | --- | --- | --- | --- | --- |
| Equipment Rental | North Park equipment on map – tents, bleachers | Equipment reserved, No electrical panel | X | Caitlin | Will need to be delivered and set-up on September 14 |
|  | Seven 4 passenger carts from Players; 1 box | Reserved | X |  | Delivery Friday by 3:00 |
|  | 6 passengers |  | X | Olivia | Got from Anderson Toyota |
|  | UPDATE MVM carts to staff and get staff only signs | Complete | X | Caitlin | Carts assigned – need to make signs |
|  | Duncan Geedes 8 pass shuttle 1 6-passenger, 1 4-passenger | Complete | X | Olivia/Patrick | Aldeen not allowed to lend us golf cart Arnie reserved them from the Park District for us |
|  | Signs for Golf carts, notes about battle pick up times |  | X | Laura |  |
|  | Order outhouses | Delivery Sept.17 | X |  | 20 reg, 2 handicap, 5 sinks, service Sat and Sun before 10am -- dropped off on Thursday, Sept 16th. |
|  | Order firewood, straw, hay | Tim/Lowell Fitch | X | Caitlin | Order closer to event, weather dependent |
|  | Confirm ATMS |  | X |  | Friday drop off |
| Friday Party-5 pm |  |  |  |  |  |
|  | St. Stanislaus Food |  | X | Caitlin | Met with Margaret, just need to give her the menu |
|  | Create Registration for reenactors |  | X | Caitlin | Fare harbor? |
|  | Signs at gates – private event |  |  |  |  |
| Emergency Services | Book medic |  | X |  |  |
|  | Book ambulance for battlefield |  |  | ? | Didn’t appear to have one in 2019 |
|  | Fire permit | Permits paid | X |  | Waiting for Pyro to send info to Fire Department |
|  | Radio assignments, cell phone lists |  | X | Caitlin | 15 Radios reserved from Rock River |
| Vendors | Invitation to vendors |  | X |  |  |
|  | Determine if waiting list vendors can get in |  | X |  | After Sept 3. |
|  | Map out vendor area |  | X |  | Done after Sept 3 |
|  | Rent tables from North Park |  | X | Caitlin | Send Number Change to North Park |
|  | Buy 4 cans of orange marking paint, painters tape for inside |  | X | Caitlin | In special events office |
|  | Sponsor booths placement | Set meeting with Oliva and Caitlin | X | Tammy/Olivia | Special Booth for Sarah Dady with water (what will we provide, what will they provide) |
|  | Golf cart sponsors shuttle |  | X | Olivia/Nancy |  |
|  | Collect vendor money | Due Sept. 3 | X | Ken/Caitlin | Most will mail in a check |
|  | Sign to ‘go upstairs for more vendors’ |  | X | Laura |  |
|  | Smoking map to reenactors, smoking area signs and receptacles, sign for staff and volunteers only for fence gate |  | X | Caitlin Cody | Caitlin will make copies for reenactors welcome packet, Maintenance will put up signs |
|  | Send email before event, spend the night Sunday??? to confirm details |  | X |  | Also to reenactors for camping in Perryville |
|  | Lonna does ads in map/program | Business card size | X | Lonna |  |
|  | Give Tammy ‘vendor check in sign’, keys, radio on Thursday– extra parking passes |  | X | Caitlin | Staying in Ralston House |
| Reenactors | Peaches reenactors attending |  | X | Caitlin | Still need to invite actual players |
|  | Registration lists to each gate. NEW SYSTEM |  | X | Caitlin | Type up for volunteer training |
|  | Insurance Certificate from HRS |  |  | Ken |  |
|  | Parking Passes and waivers | Friday of event | X | Caitlin | Copies to registration in Hospital |
| Food | Order ice – Mr. Nuckles | 815-978-3573 | X |  | Thursday, Sat before 9:30am, call if need Sunday |
|  | Confirm locations of food vendors |  | X | Caitlin |  |
|  | Confirm agreement with Papa Johns, insurance | Confirmed | X |  |  |
|  | Confirm agreement with St. Stanislaus Church, insurance, permit | Confirmed | X |  |  |
|  | Confirm agreement with Machine Shed, insurance, permit | Confirmed – need paperwork | X |  |  |
|  | Confirm agreement with Hermes, insurance, permit | Find new location | X |  |  |
|  | Confirm agreement with Pig Mind’s insurance, permit |  | X | Caitlin |  |
|  | Confirm agreement with Lulu’s Roasted Corn | Confirmed, need certificate of insurance | X | Caitlin |  |
|  | Confirm Agreement with Lemonade Shack | Confirmed – need paperwork | X | Caitlin |  |
|  | Pop and store tent placement |  | X |  |  |
|  | Volunteer lunches – pizza, served in Carlson (Courtyard) | Called to give them head’s up | X | Nancy | Drop off at noon, 11 saus, 10 ch, 11 pep each day |
|  | Purchase Volunteer pop, cups, water |  | X | Nancy |  |
| Battlefield | Audio system – Steve Knaack |  | X |  | Have been in contact, still no new number, but we are on his calendar, will be out ahead of time to reacquaint himself |
|  | Pyro purchase and permit | Scheduling demo date | X |  | Paid for permit |
|  | Sign by field entrance – reenactors with wristbands only past this point | Need to locate | X |  |  |
|  | Signs for bleachers – reserved for WWII vets | Need to locate | X |  |  |
|  | Narration |  | X |  | Committee working on |
|  | Confirm opening ceremony |  | X |  | Committee |
|  | Confirm Anthem singer |  | X | Caitlin/Nancy |  |
| Traffic and Parking | Gravel for Perryville/woods gate |  | X | Cody | Mulch |
|  | Mow battlefield, berm, bike path parking |  | X | Cody | Perryville not needed |
|  | Schedule Park Police |  | X | Arnie |  |
|  | Parking Staff schedule |  | X | Pat |  |
|  | Traffic light – Dave Fidduccia and Arnie |  | X |  | Dave called on 7/9, to be turned on starting Wed 9/15 |
| Ticketing | Members List |  |  | Olivia/Ken |  |
|  | Tent signs-member, pre-paid, etc. |  | X | Ken |  |
|  | Wristbands |  | X | Caitlin | Wristbands arrived |
|  | Media Passes |  |  | Lonna |  |
|  | Gather signs – ticketing, drones, searches, right turn, etc. | Mostly on the back dock, or in print shop | X |  |  |
|  | Pre-booked groups communication, if any | None as of 9/7 |  | Caitlin | Drop off at Main Museum, park in field – check in at lobby |
|  | Maps/programs |  |  | Lonna |  |
|  | Cashbox/Ipad List |  | X | Ken |  |
| Volunteers/Staff | Training Meeting or Video |  | X | Nancy/Caitlin |  |
|  | Wristbands and Parking Passes |  | X | Caitlin/Nancy | Neon green for volunteers |
|  | Juniors |  | X | Holly | Has 4 scheduled and costumed 8/10 |
|  | Sea Cadets and ROTC, etc. |  | X | Nancy |  |
|  | Volunteer Recognition Sign Made |  | X | Nancy or Caitlin |  |
| Miscellaneous | Set-Up List |  | X | Caitlin | First draft to maintenance |
|  | Recognize veterans |  | X | Ken | Buttons – take to admission gates Veteran only bleacher |
|  | Smoking signs in smoking areas, ropes, receptacles |  | X | Maintenance | Permit received |
|  | Signs and information in buildings – close windows! |  | X | Laura | Rugs? |
|  | Come up with schedule for Gazebo Performers – Mail wristbands |  | X | Caitlin |  |
|  | schedule for planes, get wristbands, location for static display |  | X | Caitlin |  |
|  | Schedule for presenters, and move AV equipment, send wristbands |  | X | Caitlin | Church moved to lakeview |
|  | Chalkboard Signs |  |  |  | Change Times |
|  | Mosquito foggers in woods & village |  |  | Cody |  |
|  | Order extra dumpster |  | X | Cody |  |
|  | Tree Removal for Cleaning Day | Aug. 28 | X | Cody/Patrick |  |
|  | Holocaust Exhibit | Wednesday, Sept 15 | X | Laura |  |